## Sheet1
FY-99
2.0 Phase I, Tank Load, Support Equipment, LL Electronic Rack Preparations: |  |  |  |  | Labor $$ | Man-hrs | Purchases $$
2.1 Tank 2 Preparation
|  | 2.1.1 Impedance check each Drift Tube Quad |  |  | 1027 | 16
|  | 2.1.2 Design and power Drift Tube Quads |  |  | 913 | 13
|  | 2.1.3 Calibrate Pick-up Loop |  |  | 328 | 4
| 2.2 Vacuum, Install Ion pumps and pump down Tk. |  |  |  | 1313 | 24
| 2.3 RF Crowbar, modify chassis and wire in. |  |  |  | 3081 | 45
| 2.4 Frequency Control Loop, design build |  |  |  | 1932 | 26 | 450
2.5 Support Equipment
|  | 2.5.1 Remote Control 8973 Plate PS |  |  | 4431 | 64
|  | 2.5.2 Run HV Cable to 8973, design HV splice box |  |  | 8725 | 125
|  | 2.5.3 Modify Plate PS for min resistance |  |  | 1434 | 20 | 920
|  | 2.5.3 Design Plate OC detection electronics, build crowbar chassis |  |  | 910 | 18 | 500
|  | 2.5.4 Reestablish DeIonized Water Cooling System |  |  | 1094 | 20
|  | 2.5.5 Wire Monitoring System to new control HV control rack |  |  | 2155 | 29
|  | 2.5.6 Get 8973 Vacuum Pumps operating |  |  | 421 | 6
| 2.6 Project Management Fee (Phase I, 34% of total) |  |  |  | 11500 | 115
|  | PHASE I TOTALS | $41, 134.00 |  | 39264 | 525 | 1870
FY-2000
3.0 Phase II Low Level Rack, System Checkout, Test Operations
| 3.1 Low Level 3 Wide Rack | [5 empty] | 6645
|  | 3.1.1 AC distribution, rack interconnection wiring |  |  | 20021 | 286
|  | 3.1.2 Power Supplies 4CW25K, plate, bias 8973 screen |  |  | 6202 | 93 | 3815
|  | 3.1.3 Oscillator, Low Level 50W amplifiers |  |  |  |  | 10000
|  | 3.1.4 DC Filament PS for 8973 |  |  | 770 | 12
3.2 Hot Checkout of System
3.2.1 Tank Conditioning, cost rolled into Phase II Tasks
| 3.3 8973 g1\g2 modifications push power to max. limit |  |  |  | 1491 | 21
| 3.4 Tube Swap and test, each 8973 |  |  |  | 1642 | 20
4.0 Test Result and System Documentation |  |  |  |  | 1556 | 26
| 4.1 Project Management Fee (Phase II 66% of total) |  |  |  | 22374
|  | PHASE II TOTALS |  |  | 54056 | 458 | 20460
|  | FINAL PROJECT ESTIMATE: |  | 115650
vLo:70MHZ_tst
V. LoDestro